LOCALNOW

Super App for North America

Build Plan & Scaffolding Outline

18-Month Roadmap for Investor & Engineering Leadership

April 2026

# Table of Contents

# 1. Build Plan Overview & Philosophy

LocalNow is a comprehensive super app platform targeting the North American market (Canada and the United States). This document outlines an 18-month phased delivery roadmap designed to:

- Launch an MVP with food delivery within 5 months

- Expand to 6 service categories by month 10

- Build a scalable, multi-tenant platform supporting unlimited merchants and drivers

- Achieve technical excellence through monorepo architecture and CI/CD best practices

- Enable data-driven decisions via analytics and ML recommendation engine

## Business Model

LocalNow monetizes via transaction upcharges (typically 2-5% per transaction) applied to payment processing. The platform itself is free for consumers and businesses, removing adoption friction while capturing value at transaction time.

## Target Markets

- Initial: Toronto, Vancouver, Montreal, Toronto, Los Angeles, New York

- Expansion: Secondary tier-1 cities by month 12

- Scale: Nationwide rollout by month 18

# 2. Phase 0: Foundation (Months 1–2)

Establish the technical backbone required for all subsequent phases. This phase focuses on infrastructure, CI/CD, authentication, and design systems—essentials that every product team will depend on.

## Key Deliverables

### Monorepo Architecture & Tooling

- Turborepo or Nx.dev for monorepo management

- Consistent tooling: TypeScript, ESLint, Prettier

- Shared workspace configuration and scripts

### CI/CD Pipeline & Infrastructure

- GitHub Actions or GitLab CI for automated testing and deployment

- Infrastructure-as-Code: Terraform for AWS provisioning

- Docker containerization for all services

- Kubernetes cluster ready for staging and production

### Authentication & User Service

- OAuth 2.0 + JWT-based identity service

- Multi-role support: Consumer, Merchant, Driver, Admin

- Email + phone OTP verification

- Session management and refresh token rotation

### Core Database Architecture

- PostgreSQL as primary OLTP database

- Redis for caching, sessions, and real-time data

- Elasticsearch for full-text search (restaurants, services, etc.)

- Database migrations framework (Flyway or similar)

### Design System & Component Library

- Shared React/React Native component library

- Consistent branding: Colors, typography, spacing

- Storybook documentation for all components

### Stripe Connect Integration (Skeleton)

- Merchant account onboarding workflow

- Payment processing backend integration

- Payout reconciliation framework

## Team Requirements

- 1 DevOps/Infrastructure Engineer

- 2 Backend Engineers (NestJS/Node.js)

- 1 Frontend Engineer (Design System)

# 3. Phase 1: MVP — Food Delivery (Months 2–5)

Launch a fully functional food delivery platform with consumer, merchant, and driver-facing applications. This phase validates the core business model and establishes product-market fit.

## Consumer Mobile App

- Browse restaurants and menus with filters (cuisine, rating, delivery time)

- Place orders with full menu customization

- Payment via Stripe (card, digital wallet)

- Real-time order tracking via WebSocket

- Push notifications for order status updates

- In-app chat with merchant and driver

## Merchant Dashboard

- Menu management (add/edit/delete items)

- Order acceptance/rejection workflow

- Real-time order queue visualization

- Earnings and transaction reporting

- Operating hours and availability settings

## Driver App

- Accept delivery offers with earnings transparency

- Turn-by-turn navigation with Google Maps integration

- Pickup/delivery confirmation workflow

- Daily earnings summary and withdrawal options

## Admin Panel Basics

- Merchant onboarding and approval workflow

- Driver KYC verification and activation

- Order monitoring and support ticketing

## Technical Implementation

- Order Service: Full CRUD, state machine for order lifecycle

- Payment Service: Stripe Connect integration for transaction processing

- Delivery Service: Geolocation tracking, driver matching algorithm

- Notification Service: SMS + email + push notifications

## Team Requirements

- 2 iOS/Android Engineers (React Native)

- 2 Backend Engineers (NestJS)

- 1 Frontend Engineer (Next.js dashboards)

- 1 QA Engineer

# 4. Phase 2: Local Services & Reviews (Months 5–7)

Introduce local services marketplace (haircuts, plumbing, tutoring, etc.) with reviews and appointment booking.

## Key Features

- Business listings and search with geolocation

- Reviews and ratings system (5-star, photos, responses)

- Service booking and appointment scheduling

- Merchant profile and claim-your-business feature

- Service provider directory with time slot management

## Technical Implementation

- Review Service: Moderation, spam detection, helpfulness ranking

- Booking Service: Appointment slots, calendar integration

- Search Service: Elasticsearch for faceted search (category, rating, availability)

# 5. Phase 3: Hotel/Travel & Entertainment (Months 7–10)

Add hotel search, booking, and entertainment ticketing (movies, events).

## Key Features

- Hotel search and price comparison

- Booking integration with property management systems

- Movie and event ticket booking (Ticketmaster, local venues)

- Group deals and flash sales engine

- Trip planning and itinerary builder

# 6. Phase 4: Grocery & Ride-Hailing (Months 10–14)

Launch grocery delivery and ride-hailing services.

## Key Features

- Grocery store integration with real-time inventory

- Ride-hailing with driver matching and price estimation

- Bike and scooter sharing integration

- Multi-service cart (book ride + grab groceries)

# 7. Phase 5: Scale & Optimize (Months 14–18)

Mature the platform with ML, advanced analytics, loyalty programs, and multi-city operations.

## Key Features

- ML recommendation engine (personalized suggestions, demand forecasting)

- Advanced analytics dashboard (GMV, CAC, LTV, retention cohorts)

- Loyalty program and subscription tiers

- Multi-city operations toolkit and localization

- A/B testing framework and experimentation platform

# 8. Complete Scaffolding Outline

Below is the full directory tree and architectural structure for the LocalNow monorepo.

## Monorepo Structure

localnow/
├── apps/
│   ├── consumer-mobile/     (React Native - iOS & Android)
│   ├── merchant-dashboard/  (Next.js 13+)
│   ├── driver-app/          (React Native)
│   ├── admin-panel/         (Next.js 13+)
│   └── web/                 (Next.js 13+ - consumer web)
├── packages/
│   ├── ui/                  (Shared component library)
│   ├── config/              (Shared configs: ESLint, Prettier, TypeScript)
│   ├── types/               (Shared TypeScript types & interfaces)
│   └── utils/               (Shared utilities & helpers)
├── services/
│   ├── api-gateway/         (Kong or Express gateway)
│   ├── user-service/        (NestJS - auth, profiles, preferences)
│   ├── merchant-service/    (NestJS - merchant management)
│   ├── order-service/       (NestJS - order lifecycle, state machine)
│   ├── payment-service/     (NestJS + Stripe, transaction processing)
│   ├── delivery-service/    (Go - geolocation, real-time tracking)
│   ├── search-service/      (NestJS + Elasticsearch)
│   ├── notification-service/(NestJS - SMS, email, push)
│   ├── review-service/      (NestJS - moderation, ratings)
│   ├── booking-service/     (NestJS - appointments, reservations)
│   ├── analytics-service/   (Python - data pipeline, ETL)
│   └── ml-service/          (Python - recommendations, forecasting)
├── infrastructure/
│   ├── terraform/           (IaC for AWS provisioning)
│   │   ├── rds.tf           (PostgreSQL database)
│   │   ├── elasticache.tf   (Redis cluster)
│   │   ├── eks.tf           (Kubernetes cluster)
│   │   ├── s3.tf            (Storage for user photos, documents)
│   │   ├── iam.tf           (IAM roles and policies)
│   │   └── variables.tf
│   ├── kubernetes/
│   │   ├── namespace.yaml
│   │   ├── deployments/
│   │   ├── services/
│   │   ├── configmaps/
│   │   └── secrets/
│   └── docker/
│       ├── Dockerfile.node
│       ├── Dockerfile.go
│       ├── Dockerfile.python
│       └── docker-compose.yml
├── tools/
│   ├── scripts/
│   │   ├── bootstrap.sh
│   │   ├── migrate-db.sh
│   │   └── seed-data.sh
│   └── generators/
│       ├── service-generator/
│       └── api-client-generator/
├── .github/
│   └── workflows/
│       ├── ci.yml
│       ├── cd-staging.yml
│       └── cd-production.yml
├── docs/
│   ├── architecture.md
│   ├── api-design.md
│   ├── deployment.md
│   └── onboarding.md
├── turbo.json            (Turborepo configuration)
├── package.json
├── tsconfig.json
├── .eslintrc.js
├── .prettierrc
└── README.md

## Service Layer Breakdown

| Service | Responsibility | Tech Stack |
| --- | --- | --- |
| User Service | Authentication, profiles, preferences, roles | NestJS, PostgreSQL, Redis |
| Order Service | Order lifecycle, state machine, fulfillment | NestJS, PostgreSQL, RabbitMQ |
| Payment Service | Payment processing, Stripe Connect, reconciliation | NestJS, PostgreSQL, Stripe API |
| Delivery Service | Real-time tracking, driver matching, navigation | Go, PostgreSQL, Redis, Google Maps |
| Search Service | Full-text search, faceted search, filtering | Elasticsearch, NestJS, Redis |

# 9. Team Hiring Timeline per Phase

| Phase | Timeline | Headcount | Roles |
| --- | --- | --- | --- |
| Phase 0 | Month 0-2 | 4 | DevOps, Backend, Frontend |
| Phase 1 | Month 2-5 | 10 | Mobile, Backend, QA |
| Phase 2-3 | Month 5-10 | 15 | Backend, Product, Analytics |
| Phase 4-5 | Month 10-18 | 20 | ML, Data, Operations |

# 10. Technical Milestones & Dependencies

| Milestone | Target | Dependencies |
| --- | --- | --- |
| Phase 0 Complete | End Month 2 | Infra, Auth, DB, Design System |
| MVP Launch | End Month 5 | Phase 0 complete, all services deployed |
| Services Complete | End Month 10 | Review, booking, payment services live |
| Scale Ready | End Month 18 | ML, analytics, loyalty systems |

# 11. Quality Assurance Strategy

## Testing Pyramid

- Unit Tests: 60% coverage minimum (Jest for JS, pytest for Python)

- Integration Tests: API contract testing with Pact

- E2E Tests: Critical user journeys (order placement, payment, delivery)

- Load Testing: Locust.io for stress testing order and payment services

## Continuous Quality Checks

- SonarQube for code quality metrics

- OWASP Dependency Check for security vulnerabilities

- Performance monitoring with DataDog or New Relic

- Error tracking with Sentry

## Release Process

- Semantic versioning (major.minor.patch)

- Blue-green deployments for zero-downtime releases

- Feature flags for gradual rollouts (LaunchDarkly or custom)

- Rollback procedures automated in CI/CD

# 12. Risk Mitigation for Each Phase

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Talent recruitment | Schedule slip, quality issues | Early recruiting, equity comp, strong culture |
| Technical debt | Slower iterations, outages | Code reviews, testing, refactoring time |
| Regulatory | Operations halt, legal fees | Legal counsel, compliance audits |
| Market competition | Reduced market share, lower CAC | Focus on differentiation, speed, network effects |

# 13. Success Metrics & KPIs

## Business Metrics

- Monthly Active Users (MAU)

- Gross Merchandise Value (GMV)

- Customer Acquisition Cost (CAC)

- Lifetime Value (LTV)

- Network retention: 30-day, 90-day cohorts

## Technical Metrics

- API response time < 500ms (p99)

- 99.9% uptime SLA

- Code coverage > 70%

- Mean Time to Recovery (MTTR) < 15 minutes

## User Experience Metrics

- App store rating > 4.5 stars

- Order completion rate > 95%

- Average delivery time within SLA

# 14. Conclusion

The LocalNow 18-month roadmap is designed to deliver a world-class super app platform capable of competing with market leaders. By following a phased approach, we minimize technical debt, validate product-market fit early, and scale efficiently with a lean team.

Success depends on:

- Strong foundational architecture (Phase 0)

- Rapid MVP delivery (Phase 1)

- Strategic hiring aligned with product roadmap

- Data-driven decision-making and continuous optimization

- Maintaining technical excellence and operational discipline

With disciplined execution, LocalNow will establish itself as the leading super app for North American consumers and businesses.